## Document Tracker
BRAND DOCUMENT COLLECTION TRACKER
S.No | Brand | Term Sheet | Agreement | FSSAI | Sales Data | Menu | PDC | Employee List | Medical | Police Verification | Remarks
1 | Milkbar | Done | Done | Done | Done | Done | Pending | Done | Done | Done | to be completed this week, needs regular followup | petpooja - integrated in the app | mail done | cheque book not recieved yet | m | updated items not prices
2 | Big Bear | Done | Done | Done | Done | Done | Done | Done | Done | Done | Docs Completed | petpooja - integrated in the app | mail done | PDC ready - handing over to pawan sir | m | updated items not prices
3 | BBF | Pending | Pending | Pending | Done | Done | Pending | Done | Pending | Pending | I have recived the employee aadhar cards but no medicals and police verification | petpooja - payment link sent
4 | Koby's | Done | Done | Done | Done | Done | Done | Done | Done | Done | Docs Completed | rista |  | PDC ready - call 4:30 pm around also need reciveing | m
5 | Eggspert | Done | Pending | Pending | Done | Done | Not Req | Done | Pending | Pending | PDC not required | rista |  | PDC not needed | m | can provide it by monday menu needs to be completly changed
6 | Chatpata Affair | Done | Done | Done | Done | Done | Pending | Done | Pending | Pending | PDC followup abhishek sir, signed termsheet not present but agreement is signed and completed , Medicals and PV pending | royal pos
7 | The Coffee Vault | Done | Done | Done | Done | Done | Done | Pending | Pending | Pending | Sales Data, Menu, Employee list, medical, police verification are left | petpooja - payment link sent | mail done | PDC recieved | m | updated items not prices
8 | Og Pizza | Done | Done | Done | Done | Done | Pending | Done | Done | Done | inform abhishek sir | petpooja - integrated in the app | mail done |  | m
9 | The Momo Box | Pending | Pending | Pending | Done | Pending | Pending | Done | Pending | Pending | Same as BBF | petpooja - payment link sent
10 | Burrito Bros | Done | Done | Done | Done | Pending | Pending | Done | Done | Pending | Menu will be provided by wasim sir, PDC ready , PV also in process | petpooja - integrated in the app | mail done | Bank account opened but cheque book not recieved yet
11 | Soul Crumb | Pending | Pending | Pending | Done | Pending | Pending | Pending | Pending | Pending | I was told not to contact them so no updates from them | petpooja
BRAND DOCUMENT COLLECTION TRACKER – NEW SITE
S.No | Brand | Term Sheet | Agreement | FSSAI | Sales Data | Menu | PDC | Employee List | Medical | Police Verification | Remarks
1 | Momo Box | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
2 | The Coffee Vault | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
3 | Chatpata Affair | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
4 | Sardar Ji | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
5 | Adige | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending